## Sheet1
Project
Yearly plan to complete the below Projects 1.Data Modelling with Postgres 2.Data Modelling with Apache Casandra 3.Build an Azure Datawarehouse for Bike share Data Analytics 4.Buils Azure Datalake for bike share data analytics 5.Build Data Integration Pipelines for NYC Payroll Data Analytics 6.Build CI/CD pipeline using Azure pipelines.
Week | Task | Difficulty | Quarter
2022-01-07 | Analyze Song Dataset and Log Dataset | 2 | Q1
2022-01-14 | Design and Create ERD | 2 | Q1
2022-01-21 | Create Fact and Dimension Tables | 2 | Q1
2022-01-28 | Write ETL scripts | 3 | Q1
2022-02-04 | Write ETL scripts | 3 | Q1
2022-02-11 | Write ETL scripts | 3 | Q1
2022-02-18 | Demo the project | 1 | Q1
2022-02-25 | Collect Feedback and work on Feedback | 2 | Q1
2022-03-04 | Project2 - Datamodelling with Cassandra | 2 | Q1
2022-03-11 | Design and Create ERD | 3 | Q1
2022-03-18 | Create Fact and Dimension Tables and ETL scripts | 3 | Q1
2022-03-25 | Demo the project | 1 | Q1
2022-04-01 | Analyze the Datawarehouse and Datalake project | 2 | Q2
2022-04-08 | Prepare ERD for the project based on star schema | 3 | Q2
2022-04-15 | Upload the source data to azure blob | 1 | Q2
2022-04-22 | Create External tables | 2 | Q2
2022-04-29 | Load data into Fact and Dim tables in Synapse | 3 | Q2
2022-05-06 | Import the data into Azure Databricks using Delta Lake to create a Bronze data store | 3 | Q2
2022-05-13 | Create a gold data store in Delta Lake tables; | 3 | Q2
2022-05-20 | Transform the data into the star schema for a Gold data store; | 3 | Q2
2022-05-27 | Demo the project and work on Feedback | 2 | Q2
2022-06-03 | Analyze DataIntegration Project with Azure pipelines | 2 | Q2
2022-06-10 | Create the data lake and upload data | 2 | Q2
2022-06-17 | Create an Azure Data Factory Resource | 3 | Q2
2022-06-24 | Create a SQL Database to store the current year of the payroll data | 3 | Q2
2022-07-01 | Create A Synapse Analytics workspace, or use one you already have created. |  | Q3
2022-07-08 | Create Linked services | 3 | Q3
2022-07-15 | Create Linked services | 3 | Q3
2022-07-22 | Create Linked services | 3 | Q3
2022-07-29 | Create Datasets | 3 | Q3
2022-08-05 | Create Datasets | 3 | Q3
2022-08-12 | Create Datasets | 3 | Q3
2022-08-19 | Create Dataflows | 3 | Q3
2022-08-26 | Create Dataflows | 3 | Q3
2022-09-02 | Create Dataflows | 3 | Q3
2022-09-09 | Create Data Aggregation | 2 | Q3
2022-09-16 | Connect the Project to github | 1 | Q3
2022-09-23 | Demo the project and collect feedback | 2 | Q3
2022-09-30 | Work on Feedback | 2 | Q3
2022-10-07 | Analyse CI/CI pipeline project | 2 | Q4
2022-10-14 | Create Project plan | 3 | Q4
2022-10-21 | Setup Azure Cloud shell | 3 | Q4
2022-10-28 | Setup Azure Cloud shell | 3 | Q4
2022-11-04 | Setup Azure Cloud shell | 3 | Q4
2022-11-11 | Configure github actions | 2 | Q4
2022-11-18 | Configure github actions | 3 | Q4
2022-11-25 | Configure github actions | 2 | Q4
2022-12-02 | Configure github actions | 3 | Q4
2022-12-09 | Continuous delivery | 3 | Q4
2022-12-16 | Continuous delivery | 3 | Q4
2022-12-23 | Documentation | 2 | Q4
2022-12-30 | demo and feedback | 2 | Q4
2022-12-16 | Goals | Goals
Q1 | Datamodelling projects completed in Postgres and apache Cassandra
Q2 | Build datawarehouse and Datalake projects
Q3 | Complete Azure data integration project
Q4 | Complete Azure Datapipeline project with CI/CD